## ATPL-20201026-YallaGamers
Yalla Gamers Mobile App
|  | GANTT Chart : Yalla Gamers Mobile App Release ID: Augurs Tech: Protected Controlled Copy Project ID:ATPL-20201026-YallaGamers-Mobile-App <SCI.ID.> / Ver: 1.1 |  | Resources | Dev 1
Dev2
[5 empty] | Project Start Date | 2020-03-06 |  | March | [27 empty] | April | [28 empty] | May | [30 empty] | June
 | time axis 2020-03-06 to 2020-08-30
S# | Requirement ID | Task Description | Milestone | Resource | Weekday Duration | Start | End | time axis 2020-03-06 to 2020-08-30
1 |  | >Project Setup >Home, category, item list, item details, login, signup screens design >Web API setup, Home screen category design setup in app |  | Dev 1 | 5 | 2020-03-06 | 2020-03-12
2 |  | Home Page >Home screen category list data from API >Home screen item list data from API >Categories list screen functional implementation >Items List Screen functional implementation |  | Dev 1 | 10 | 2020-03-13 | 2020-03-26
3 |  | Items > Sorting Items > Searching Item > Items details screens with all functional implementation including wishlist and add to cart functions |  | Dev 1 | 6 | 2020-03-27 | 2020-04-05
4 |  | Special categories and cart management > Playstation, XBOX, Nintendo screens functional implementation > Cart management |  | Dev 1 | 10 | 2020-04-06 | 2020-04-19
5 |  | Shipping and Checkout > Shipping and checkout page screen design > Shipping and checkout page functional implementation with Order Summary, save card and redeem points options |  | Dev 1 | 12 | 2020-04-20 | 2020-05-05
6 |  | Payment gateway > User Login/Signup > Payment gateway integration > Process order and order details screen |  | Dev 1 | 10 | 2020-05-06 | 2020-05-19
7 |  | My Account Page > Order List > Wish List > Comparision List |  | Dev 1 | 10 | 2020-05-20 | 2020-06-02
8 |  | UAT Project Handholding |  | Dev 1 | 5 | 2020-06-03 | 2020-06-09
0
Holiday
[5 empty] | 2021-01-01 | 2021-01-01
[5 empty] | 2021-01-14 | 2021-01-14